Hope HR System

Team Progress Report — FINAL

Sprint 1, 2 & 3 — All Roles M1 to M5

As of May 21, 2026 | 70+ PRs Merged | GitHub: nhicavalderas/InfoManFinalProject2026

# Overall Team Progress Summary

| Role | Member | PRs Merged | Sprint 1 | Sprint 2 | Sprint 3 | Overall |
| --- | --- | --- | --- | --- | --- | --- |
| M1 — Project Lead | Nhica Valderas | ~14 | DONE | DONE | DONE | 100% |
| M2 — Frontend Dev | Jovin Lowell Dula | ~20 | DONE | DONE | DONE | 100% |
| M3 — DB Engineer | Jhunelle Remo | ~15 | DONE | DONE | DONE | 98% |
| M4 — Rights & Auth | Shpsall | ~6 | DONE | DONE | DONE | 80% |
| M5 — QA & Docs | JM Belen | ~5 | DONE | DONE | IN PROGRESS | 70% |

# Issues Log & Fixes (Complete History)

| Issue | Who Fixed | Fix Applied | Status |
| --- | --- | --- | --- |
| Vercel 404 on page refresh | M2 | Added vercel.json with rewrite rule — PR #58 | DONE |
| dev → main not merged — old UI on Vercel | M1/M2 | PR #59 — conflict resolved, merged to main | DONE |
| AuthContext.jsx merge conflict PR #57 | M2 | Accepted incoming changes via GitHub web editor | DONE |
| userid mismatch — all team members | M2 | SQL UPDATE synced all auth IDs in UserModule_Rights and user table | DONE |
| M1 nhica.valderas@neu.edu.ph — duplicate row conflict | M2 | Deleted old seeded row, inserted with correct auth UUID, re-seeded 17 rights | DONE |
| j-m.belen UUID collision with aqlussalim | M2 | Manual SQL UPDATE with correct auth UUID for both tables | DONE |
| Employee list missing Dept, Job Code, Status columns | M2 | Switched API to query employee_current_job view — PR #60/64 | DONE |
| Job descriptions and department names empty | M2 | Seeded jobdesc and deptname via SQL UPDATEs | DONE |
| Missing employee (John Smith) in list — no job history | M2 | Inserted job history record and fixed record_status to ACTIVE | DONE |
| Duplicate Add Record button in Job History | M2 | Removed ungated duplicate button — PR #65 | DONE |
| Column name casing mismatch (deptCode vs deptcode) | M2 | Fixed keys in EmployeeListPage, JobHistoryPage, JobsPage, DepartmentsPage | DONE |
| White screen crash — ReferenceError: W is not defined | M2 | Fixed bad variable reference in EmployeeListPage — PR #68/70 | DONE |
| No sortable columns on Employee and Job History | M2 | Added click-to-sort on all column headers with ↑↓↕ indicators — PR #67/68 | DONE |
| USER role showing Add/Edit buttons (should be view-only) | PENDING | Rights SQL update needed for USER type accounts | PENDING |
| No job history data seeded for professor demo | M3 | Needs seeding in HopeDB — required for delete demo | PENDING |
| user_module foreign key constraint dropped during sync | M3 | Needs to be re-added properly after userid sync | PENDING |

M1 — Project Lead — Nhica Valderas

## Sprint 1 — Project Setup & GitHub

| PR # | Task | Status |
| --- | --- | --- |
| #1 | Add React Router v6 with ProtectedRoute | DONE |
| #3 | Add project scaffold with Vite, React, Tailwind and README | DONE |
| #4 | Add Supabase client initialization | DONE |
| #5 | Add branch protection rules for main and dev | DONE |
| #12 | Add route guard for deleted items page | DONE |

## Sprint 2 — API & Deployment

| PR # | Task | Status |
| --- | --- | --- |
| #9 | Wire employee API service functions | DONE |
| #10 | Wire job history API service functions | DONE |
| #11 | Wire job and department API service functions | DONE |
| #13 | Wire admin API service functions | DONE |
| #14 | Wire reports API service functions | DONE |
| #37 | Add Vercel deployment configuration | DONE |
| #38 | Add Vercel production deploy | DONE |

## Sprint 3 — Completed

| PR # | Task | Status |
| --- | --- | --- |
| #57 | Resolve AuthContext.jsx merge conflict via GitHub web editor | DONE |
| #59 | Merge dev → main — conflict resolved, final production deployment | DONE |
| Multiple | Approve and merge PRs #58, #60, #64, #65, #66, #67, #68, #70 to keep main updated | DONE |

✅ M1 Sprint 3 COMPLETE — All deployment and conflict resolution done.

M2 — Frontend Developer — Jovin Lowell Dula

## Sprint 1 — UI Shell & Auth Pages

| PR # | Task | Status |
| --- | --- | --- |
| #2 | feat/ui-sprint1-m2 — Add Sprint 1 complete frontend UI | DONE |
| #7 | feat/ui-employee-detail-jh — EmployeeDetailPage with embedded JobHistoryPanel | DONE |
| #8 | fix: use M2 full pages in App.jsx, add AppShell Outlet, wrap with AuthProvider | DONE |
| #15 | chore: remove duplicate blank page files created by M1 | DONE |

## Sprint 2 — Real API Wiring & Design

| PR # | Task | Status |
| --- | --- | --- |
| #18 | feat: wire real Supabase API into EmployeeListPage | DONE |
| #36 | feat: wire real Supabase API into Jobs, Departments, JobHistory, DeletedItems | DONE |
| #39 | feat: redesign login page with glassmorphism UI and hope color system | DONE |
| #40 | feat: wire real Supabase API into EmployeeDetailPage and JobHistoryPanel | DONE |
| #41 | feat: build Admin user management page with activate/deactivate and stats cards | DONE |
| #49 | feat: sync M4 complete AuthContext and useRights from main to dev | DONE |
| #50 | feat: apply rights gating to all CRUD buttons and sidebar using useRights() | DONE |

## Sprint 3 — All Completed

| PR # | Task | Status |
| --- | --- | --- |
| #51 | feat: show real username and role in Navbar from AuthContext | DONE |
| #52 | feat: hide stamp column from USER role, visible only to ADMIN and SUPERADMIN | DONE |
| #58 | fix: add vercel.json for client-side routing — fixes 404 on page refresh | DONE |
| #59 | chore: merge dev to main for production deployment | DONE |
| #60 | fix: use employee_current_job view to show dept, job, status in employee list | DONE |
| #64 | chore: final sync dev to main — employee view fix and column name corrections | DONE |
| #65 | fix: remove duplicate Add Record button and fix column name casing in JobHistory, Jobs, Departments | DONE |
| #66 | chore: final sync dev to main — jobhistory fixes and column name corrections | DONE |
| #67 | feat: add sortable columns to Employee and Job History tables (click headers to sort) | DONE |
| #68 | feat: add sortable columns merged to main — live on Vercel | DONE |
| #70 | fix: resolve ReferenceError W is not defined — fixed white screen crash on Vercel | DONE |
| — | Fixed Supabase userid mismatch for ALL team members via SQL (M1, M5, nhica, aqlussalim conflict) | DONE |
| — | Seeded job descriptions, department names, employee job history via Supabase SQL | DONE |
| — | Seeded 17 rights for all team members in UserModule_Rights | DONE |

✅ M2 is 100% COMPLETE — 20+ PRs merged, all deployment, data, and UI fixes done. Outstanding work!

M3 — DB Engineer — Jhunelle Remo

## Sprint 1 — Database Schema & Triggers

| PR # | Task | Status |
| --- | --- | --- |
| #16 | feat(m3): add initial HopeDB schema migration | DONE |
| #17 | feat(m3): add record status and stamp columns | DONE |
| #19 | feat(m3): fix provision new user trigger | DONE |
| #20 | Feature/m3 s1 04 user rights schema | DONE |
| #21 | feat(m3): add user modules and rights schema | DONE |
| #22 | Feature/m3 s2 01 employee rls | DONE |
| #24 | feat(m3): add employee status cascade trigger | DONE |

## Sprint 2 — RLS Policies & Views

| PR # | Task | Status |
| --- | --- | --- |
| #26 | feat(m3): add jobhistory RLS policies | DONE |
| #27 | feat(m3): add job RLS policies | DONE |
| #28 | feat(m3): add department RLS policies | DONE |
| #29 | Feature/m3 s3 report views clean | DONE |
| #30 | Feature/m3 s3 admin rls clean | DONE |
| #31 | Feature/m3 final verification clean | DONE |
| #32 | test(m3): add final database verification script | DONE |

## Sprint 3 — Remaining Tasks

| Task | Status | Notes |
| --- | --- | --- |
| Seed job history records in HopeDB | PENDING | No job history data — required for professor demo of delete function |
| Re-add user_module foreign key constraint | PENDING | Dropped during userid sync — needs to be re-added |
| Verify cascade triggers with real data | PENDING | Test after job history data is seeded |

M4 — Rights & Auth — Shpsall

## Sprint 1 — AuthContext & Login

| PR # | Task | Status |
| --- | --- | --- |
| #42 | Fix/auth context complete | DONE |
| #43 | feat: add AuthCallbackPage with error handling | DONE |
| #44 | feat: complete Sprint 1 — AuthContext, useRights, login, registration | DONE |
| #35 | PR-01: AuthContext with session listener and rights loading | DONE |

## Sprint 2 & 3 — Rights Gating Status

| Task | Status | Notes |
| --- | --- | --- |
| useRights() hook — hasRight(), isAdmin, isSuperAdmin | DONE | Merged via PR #44 |
| Login guard — INACTIVE users blocked | DONE | Alert shown, redirected to login |
| 17 rights loaded from UserModule_Rights on login | DONE | Confirmed in AuthContext |
| Google OAuth — @neu.edu.ph only | DONE | org_internal configured in Supabase |
| Navbar shows real user name and role | DONE | Fixed by M2 in PR #51 |
| USER role rights gating — Add/Edit buttons hidden | PENDING | USER accounts not yet in DB — rights SQL fix needed when USER signs up |
| SUPERADMIN cannot be deactivated — live test | PENDING | Needs test with teacher/professor account |

M5 — QA & Documentation — JM Belen

## Sprint 1 & 2 — QA Test Cases

| PR # | Task | Status |
| --- | --- | --- |
| #33 | Sprint 1: Add auth flow tests | DONE |
| #34 | Create sprint1-log.md | DONE |
| #45 | Sprint 2: Add 51-case rights matrix tests | DONE |
| #46 | Sprint 2: Add cascade soft-delete and stamp visibility tests | DONE |
| #47 | Sprint 2: Add sprint log documentation | DONE |
| #48 | Sprint 3: Add production E2E test checklist | DONE |

## Sprint 3 — Remaining Tasks

| Task | Status | Notes |
| --- | --- | --- |
| Run all 51 rights test cases with real accounts | PENDING | All accounts now active and Vercel is live — can start NOW |
| Document test results (PASS / FAIL / BLOCKED) | PENDING | Use testing sheet template from M5 guide |
| Report bugs to responsible team members | PENDING | M3 still needs to seed job history for delete test |
| Write user manual | PENDING | See M5 Guide document for outline |
| Complete 12-slide presentation | PENDING | Take screenshots from live Vercel — site is NOW fully working |
| Final QA report submitted to group | PENDING | Before submission deadline |

# Remaining Action Items Before Presentation

| Priority | Who | What to Do |
| --- | --- | --- |
| 1 — URGENT | M3 | Seed job history records in HopeDB so professor can demo the delete function |
| 2 — URGENT | M2 | Fix USER role rights — Add/Edit buttons should be hidden for USER type accounts |
| 3 — HIGH | M5 | Run all 51 test cases on live Vercel with real accounts and document results |
| 4 — HIGH | M5 | Take screenshots from live Vercel for 12-slide presentation |
| 5 — MEDIUM | M3 | Re-add user_module foreign key constraint dropped during userid sync |
| 6 — MEDIUM | M4 | Test SUPERADMIN cannot be deactivated with professor account |

# GitHub Repository & Live Site Summary

| Metric | Value |
| --- | --- |
| Total PRs Merged | 70+ (as of May 21, 2026) |
| Repository | github.com/nhicavalderas/InfoManFinalProject2026 |
| Live URL | https://info-man-final-project2026.vercel.app |
| Live URL Status | ✅ FULLY LIVE — New UI, all accounts working, routing fixed, sortable tables |
| Features Working on Vercel | Login (Google OAuth), Employee list with dept/job/status, Job History with salary sort, Jobs, Departments, Admin panel, Rights gating by role |
| Main Branch | Final production code — all PRs merged as of May 21, 2026 |
| Open PRs | 0 open — all merged |

Hope HR System — Final Team Progress Report | May 21, 2026 | Prepared for presentation